TOOL

Monthly customer report - Summary Type

by Jean-Pierre Payre

This tool proposes a standard summary of the monthly report to be sent to the customer to inform him of the project's progress.

MONTHLY REPORT SUMMARY

1	summary	4

1.1	STATUS OF WORK	4

1.2	PLANNING STATUS	4

1.3	OTHER IMPORTANT TOPICS	4

2	current activities	5

2.1	ENGINEERING AND DESIGN	5

2.1.1	Work package n°1	5

2.1.2	Work package no. 2	5

2.1.3	Work package no. 3	5

2.1.4	Work package no. 4	5

2.2	PROCUREMENT, MANUFACTURING AND TRANSPORT	6

2.2.1	Work package n°1	6

2.2.2	Work package n°2	6

2.2.3	Work package no. 3	6

2.2.4	Work package n°4	6

2.3	ASSEMBLY	7

2.3.1	Work package n°1	7

2.3.2	Work package n°2	7

2.3.3	Work package no. 3	8

2.3.4	Work package n°4	8

2.4	COMMISSIONING AND TESTING	8

2.5	TRAINING ACTIVITIES 	8

2.6	HYGIENE AND SAFETY	8

2.7	ENVIRONMENTAL ISSUES	9

2.8	QUALITY ASSURANCE AND CONTROLS	9

3	STATUS OF PLANNING AND COSTS	10

3.1	PLANNING	10

3.2	COSTS	12

3.2.1	Billing and payment status	12

3.2.2	Status of endorsements	12

3.2.3	Statement of contractual differences	13

4	projected activities for the next period	14

4.1	ENGINEERING AND DESIGN	14

4.1.1	Work package n°1	14

4.1.2	Work package no. 2	14

4.1.3	Work package no. 3	14

4.1.4	Work package no. 4	14

4.2	PROCUREMENT, MANUFACTURING AND TRANSPORT	14

4.2.1	Work package n°1	14

4.2.2	Work package no. 2	14

4.2.3	Work package no. 3	14

Techniques de l'Ingénieur

4.2.4	Work package no. 4	15

4.3	ASSEMBLY	15

4.3.1	Work package n°1	15

4.3.2	Work package n°2	15

4.3.3	Work package no. 3	15

4.3.4	Work package no. 4	15

4.4	TESTING AND COMMISSIONING	15

5	APPENDICES	15

5.1	schedule of in-process inspections and forthcoming controls	16

5.2	planning chart (project s-curves)	16

5.3	project milestone schedule (planned vs. actual)	16

5.4	critical path analysis	16

5.5	payment schedule	16

5.6	document submission list, planned and actual	16

5.7	status of subcontracting orders	16

5.8	delivery schedule	16

5.9	sub-assembly inspection reports (for the month and forecast for the following months)	16

5.10	photographic documentation	17

5.10.1	manufacturing progress photos	17

5.10.2	on-site progress photos	17

5.11	status of endorsements	18

5.12	list of correspondences and status	22

5.13	action plan planning (if activities are behind schedule), acceleration measures, etc.)	23

© Techniques de l'Ingén ieur