TOOL

Variance and performance indicators and forecast calculation

by Jean-Pierre Payre

This tool uses tables to list variance and performance indicators, and provides formulas for calculating forecasts.

VARIANCE AND PERFORMANCE INDICATORS AND FORECAST CALCULATION

Earned value analysis key values

| Acronyms | Indicators | Interpretation |
| --- | --- | --- |
| VP (PV) | Planned value (Planned Value) | What is the estimated value of the planned work? |
| VA (EV) | Earned value (Earned Value) | What is the estimated value of the work actually done? |
| CR (AC) | Actual cost (Actual Cost) | How much does the work actually cost? |

Techniques de l'Ingénieur

Earned value indicators

| Acronyms | Indicators | Interpretation |
| --- | --- | --- |
| PV | Planned value | Estimated value of planned work |
| EV | Earned value | Estimated value of work performed |
| AC | Actual costs | Actual cost (incurred) of work performed |
| BAC | Final budget | Budget for the entire project |
| EAC | Estimate on completion | Project cost on completion |
| ETC (RAF) | What remains to be done | Budget required to complete the project |
| VAC | Variances at end of period | Variance at end of project (over or under budget) |

Variance and performance indicators "to date

| Indicator | Formula | Interpretation |
| --- | --- | --- |
| Cost variance (Cost variance, CV) | = Earned value - Actual cost = EV - AC | Negative if the project is over budget; positive if it is under budget. |
| Delay variance (Schedule variance, SV) | = Earned value - Planned value = EV - PV | Negative if the project is behind schedule - positive if it is ahead of schedule |
| Delay performance index (Schedule performance index, SPI) | = Earned value - planned value = EV/PV | This indicator is also an "end-of-project" indicator. Progress at x% of initial forecasts |
| Cost performance index (Cost performance index, CPI) | = Earned value/Actual cost = EV/AC | This indicator is also an "end-of-project" indicator. For each € invested, I earn € xx |

The basic values of performance forecasting

| Indicator | English | Abbreviation | Interpretation |
| --- | --- | --- | --- |
| Overall budget | Budget At Completion | BAC | Project budget |
| Estimated budget to complete the project ("reste à faire") | Estimate To Complete | EAC | Estimated additional cost to complete work from reference date |

Techniques de l'Ingénieur

Forecast calculations for project variants

| Terms | Formulas to remember | Calculation of the final cost of the project, based on the project's status "to date". |
| --- | --- | --- |
| Overall cost estimate (Estimate At Completion) |  |  |
| Variant 1 | EAC = BAC/CPI | Used when the overall budget remains valid (as well as the cost performance index) |
| Variant 2 | EAC = AC + ETC | Used when the initial budget is no longer valid |
| Variant 3 | EAC = AC + BAC - EV | Used when the project budget is considered atypical for the future |
| Variant 4 | EAC = AC + (BAC-EV)/CPI | Used when the project budget is considered atypical for the future |
| Estimated remaining work (Estimate To Complete) | ETC = BAC - AC | Additional project costs |
| Cost-to-completion variances (Variance At Completion) | VAC = BAC - EAC | Evaluation of variance from initial project budget |

Techniques de l'Ingénieur

Techniques de l'Ingénieur